## Summary
EDR Testing Plan and Schedule
Reference schedule. Testing starts after required setup artifacts, access, and environment blockers are closed.
Start condition | T0 is the first business day after the missing code, configuration, database seed/login data, Fabric assets, and environment setup details are cleared.
Schedule type | Provisional reference schedule using relative business days.
Planned duration | 20 business days from T0, subject to environment stability and client-side defect resolution turnaround.
Defect resolution | Resolution of defects and gaps identified during testing is outside testing scope and requires a dedicated implementation team.
Primary deliverables | Test cases, execution evidence, defect/gap register, compliance checklists, performance results, and final report.
Phase | Relative Window | Main Test Areas | Primary Dependency | Evidence Output | Owner | Status | Notes
1 | Days 1-2 | Kickoff, dependency closure, environment build, smoke checks, traceability | All start-gate artifacts available | Readiness checklist, smoke evidence | Testing team + client technical owner | Planned | Can only begin once dependencies are cleared
2 | Days 3-6 | Security scans, DB validation, Fabric deployment, API security start | Source, SQL dump, Fabric assets, credentials | Security and setup evidence | Testing team | Planned | Parallel execution where environment is stable
3 | Days 5-10 | Web, mobile, backend/API, smart contract, consent workflow testing | Runnable frontend/mobile/API/Fabric stack | Functional and blockchain test evidence | Testing team | Planned | Blocked items move to risk log if code is unavailable
4 | Days 10-13 | Performance baseline, scaling readiness, compliance testing | Stable environment and agreed workload model | Performance and compliance checklists | Testing team + client infra owner | Planned | Autoscaling test requires Kubernetes or equivalent
5 | Days 14-17 | Defect triage and retest support | Implementation team resolves defects/gaps | Retest evidence and updated defect status | Testing team + implementation team | Planned | Fixes are not part of testing scope
6 | Days 18-20 | Final report and closure | Execution substantially complete | Final report and evidence index | Testing team | Planned | Residual risks documented
Metric | Value | Basis | Comment
Planned calendar model | Relative business days | T0 after dependency closure | Attach this schedule as planning reference

## Detailed Schedule
ID | Workstream | Test Area | Scope / Key Activities | Tools / Method | Entry Dependency | Duration (BD) | Start Day | End Day | Output / Evidence | Dependency Status
TS-01 | Mobilization | Kickoff and dependency closure | Confirm missing artifacts, setup approach, test access, roles, contacts, and acceptance criteria. | Review session, dependency tracker | Client confirms requested setup artifacts and access | 1 | 1 | 1 | Dependency tracker and entry checklist | Start gate
TS-02 | Environment | Environment build and smoke checks | Bring up database, APIs, Fabric network, frontend, and mobile app where available; validate basic service health. | Docker Compose, npm, Fabric peer CLI, curl | Docker Compose or equivalent runbook; complete Fabric files; environment variables | 2 | 1 | 2 | Smoke test evidence and environment notes | Critical path
TS-03 | Mobilization | Requirement traceability and test case finalization | Map BRD/SRS/testing requirements to test cases, evidence expectations, and pass/fail criteria. | Manual review, traceability matrix | Final documents and working application scope confirmed | 2 | 1 | 2 | Traceability matrix and test cases | Can run in parallel
TS-04 | Security | Source code and secret exposure scan | Review source for secrets, unsafe patterns, injection risks, dependency misuse, and obvious backend/API weaknesses. | Semgrep CE, Gitleaks, manual review | Complete source code repositories | 1 | 3 | 3 | Security scan evidence and findings | Requires full source
TS-05 | Security | Dependency and container image scan | Review application dependencies and available container images for known issues and outdated components. | Trivy, npm audit where applicable | Package files, lock files, Dockerfiles/images | 1 | 3 | 3 | Dependency and image scan results | Requires runnable build assets
TS-06 | Security | TLS and endpoint exposure checks | Check TLS protocol/cipher posture, certificate configuration, exposed ports, and basic HTTP security behavior. | testssl.sh, OpenSSL, curl | Target endpoints available | 1 | 4 | 4 | TLS and endpoint checklist | Environment dependent
TS-07 | Security | Authentication, authorization, and API negative testing | Validate login, JWT/session behavior, role access, invalid inputs, unauthorized access, and API error handling. | curl, OWASP ZAP, custom negative-test scripts | Stable API services and test users | 2 | 4 | 5 | API security test evidence | Requires test credentials
TS-08 | Functional | Web application functional testing | Validate admin and doctor workflows, navigation, data views, registration flows, access requests, and error states. | Manual test execution | Complete web frontend and API configuration | 3 | 5 | 7 | Web functional test results | Blocked until frontend is provided
TS-09 | Functional | Mobile application functional testing | Validate patient workflows, consent handling, request review, login, device/API configuration, and mobile error states. | Manual test execution on Expo/device or emulator | Complete mobile app source and mobile API configuration | 3 | 5 | 7 | Mobile functional test results | Blocked until mobile app is provided
TS-10 | Functional | Backend and API integration testing | Validate database API, blockchain API, cross-service calls, data creation, retrieval, sync, and error handling. | curl, custom API scripts | Database, API services, seeded data, and Fabric network running | 2 | 5 | 6 | API integration evidence | Environment dependent
TS-11 | Functional | Database validation and seed data checks | Validate schema import, seed records, login users, role mapping, referential integrity, and data consistency. | MySQL CLI, SQL queries | Validated SQL dump and MySQL version | 1 | 4 | 4 | Database validation checklist | Requires corrected seed data
TS-12 | Blockchain | Fabric network and chaincode deployment validation | Validate network startup, channel creation, chaincode deployment, connection profile, wallet identities, and peer CLI access. | Fabric peer CLI, network.sh, curl | Complete Fabric test-network assets and binaries/config | 2 | 3 | 4 | Deployment evidence and setup notes | Critical path
TS-13 | Blockchain | Smart contract review and negative tests | Review chaincode behavior, access-request state transitions, input validation, error paths, and ledger write/read behavior. | Semgrep CE, Fabric peer CLI, custom negative-test scripts | Deployed chaincode and test identities | 2 | 5 | 6 | Chaincode review and negative test evidence | Requires Fabric network
TS-14 | Blockchain | Consent workflow and ledger integrity testing | Validate Doctor to Admin to Patient consent flow, approval/rejection paths, audit trail, unauthorized data access prevention, and ledger consistency. | Fabric peer CLI, API scripts, manual workflow testing | Frontend/mobile/API/Fabric workflows available | 3 | 7 | 9 | Blockchain workflow evidence | Cross-system test
TS-15 | Performance | Load and performance baseline testing | Measure API and blockchain transaction behavior under agreed concurrency and transaction volumes; capture response times and resource usage. | Hyperledger Caliper, custom load scripts, docker stats | Stable environment, benchmark files or approved workload model | 2 | 10 | 11 | Performance baseline results | Requires stable environment
TS-16 | Performance | Horizontal scaling readiness assessment | Assess whether the provided environment can support scaling tests and document gaps where Docker Compose is insufficient for autoscaling validation. | Kubernetes-ready configuration review, docker stats, logs | Client confirms scaling test environment or acceptable substitute | 1 | 12 | 12 | Scaling readiness note and recommendation | May require updated test environment
TS-17 | Compliance | HIPAA control-oriented testing | Assess authentication, authorization, audit logging, access controls, transmission security, data minimization, and sensitive data handling evidence. | Manual compliance checklist, API/security evidence review | Stable workflows and access to logs/configuration | 2 | 11 | 12 | HIPAA testing checklist and gaps | Testing only, remediation excluded
TS-18 | Compliance | GDPR control-oriented testing | Assess consent, privacy notices where available, data access/export/deletion readiness, retention indicators, and personal data handling evidence. | Manual compliance checklist, workflow evidence review | Stable workflows and available documentation | 2 | 12 | 13 | GDPR testing checklist and gaps | Testing only, remediation excluded
TS-19 | Reporting | Defect triage and retest support | Consolidate defects, support walkthroughs, retest fixes made by the implementation team, and update evidence where applicable. | Defect tracker, retest scripts, manual verification | Implementation team available for fixes | 3 | 14 | 16 | Retest evidence and defect status | Fixing defects is out of scope
TS-20 | Reporting | Final report and closure | Prepare final testing report, executive summary, evidence index, unresolved risk register, and closing observations. | Report compilation and evidence review | Test execution substantially complete | 2 | 18 | 19 | Final test report and evidence pack | Final deliverable

## Gantt View
ID | Workstream | Test Area | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
TS-01 | Mobilization | Kickoff and dependency closure | bar: Day 1
TS-02 | Environment | Environment build and smoke checks | bar: Day 1 to Day 2
TS-03 | Mobilization | Requirement traceability and test case finalization | bar: Day 1 to Day 2
TS-04 | Security | Source code and secret exposure scan | bar: Day 3
TS-05 | Security | Dependency and container image scan | bar: Day 3
TS-06 | Security | TLS and endpoint exposure checks | bar: Day 4
TS-07 | Security | Authentication, authorization, and API negative testing | bar: Day 4 to Day 5
TS-08 | Functional | Web application functional testing | bar: Day 5 to Day 7
TS-09 | Functional | Mobile application functional testing | bar: Day 5 to Day 7
TS-10 | Functional | Backend and API integration testing | bar: Day 5 to Day 6
TS-11 | Functional | Database validation and seed data checks | bar: Day 4
TS-12 | Blockchain | Fabric network and chaincode deployment validation | bar: Day 3 to Day 4
TS-13 | Blockchain | Smart contract review and negative tests | bar: Day 5 to Day 6
TS-14 | Blockchain | Consent workflow and ledger integrity testing | bar: Day 7 to Day 9
TS-15 | Performance | Load and performance baseline testing | bar: Day 10 to Day 11
TS-16 | Performance | Horizontal scaling readiness assessment | bar: Day 12
TS-17 | Compliance | HIPAA control-oriented testing | bar: Day 11 to Day 12
TS-18 | Compliance | GDPR control-oriented testing | bar: Day 12 to Day 13
TS-19 | Reporting | Defect triage and retest support | bar: Day 14 to Day 16
TS-20 | Reporting | Final report and closure | bar: Day 18 to Day 19

## Dependencies
Dependency ID | Required Item | Current Finding | Why Needed | Required Before | Request / Action | Status
D-01 | Docker Compose file or equivalent environment automation | Not present in shared source | Required to start MySQL, APIs, Fabric services, frontend, and related containers consistently. | Before Day 1 | Client to provide compose file, service list, ports, volumes, and startup order. | Open
D-02 | Complete web frontend source code | bc-dentistry-frontend folder is empty | Required for web functional testing and end-to-end workflow validation. | Before Day 1 | Client to provide React/Vite source, package files, env example, and run command. | Open
D-03 | Complete mobile application source code | BC-Dentistry-Mobile-App folder is empty | Required for patient mobile consent workflow testing. | Before Day 1 | Client to provide Expo/React Native source or exact repo, branch, and commit. | Open
D-04 | Complete Fabric test-network assets | network.sh references compose, configtx, organizations, bin, and config assets that are not included | Required to bring up Fabric network, create channel, deploy chaincode, and generate connection profile. | Before Day 1 | Client to provide complete test-network package or confirm exact Fabric sample version/setup. | Open
D-05 | Fabric connection profile and wallet setup | connection-org1.json and wallet identities are not included | Required for blockchain API enrollment and chaincode access. | Before Day 2 | Client to provide generation commands, expected paths, and identity setup steps. | Open
D-06 | Validated database dump and seed data | datamodel2.sql has seed data but also schema mismatch indicators | Required for login, role-based testing, data views, and repeatable tests. | Before Day 1 | Client to confirm datamodel.sql vs datamodel2.sql, fix syntax issues, and include user/role/admin seed records. | Open
D-07 | Confirmed MySQL version | README/logs suggest MySQL latest/9.0.1 in prior environment | Required to avoid import and compatibility differences. | Before Day 1 | Client to confirm exact MySQL image/version used. | Open
D-08 | Environment variables and local configuration | .env.example files exist but code also contains hardcoded ports/hosts/secrets | Required for APIs, frontend, mobile LAN testing, JWT configuration, Fabric channel/chaincode, and DB connectivity. | Before Day 1 | Client to provide sanitized .env files and confirm production secrets are not shared. | Open
D-09 | Test credentials | README lists test users, but matching seed records are not fully present in datamodel2.sql | Required for Admin, Doctor, and Patient workflow execution. | Before Day 2 | Client to provide confirmed test users/passwords and expected role mappings. | Open
D-10 | Caliper benchmark files or approved workload model | caliper-benchmarks folder is empty | Required for Fabric performance testing and repeatable load tests. | Before Day 10 | Client to provide benchmark YAML/workloads or approve us to define the workload model. | Open
D-11 | Existing running environment details | Infrastructure details are not included | Required for load testing assumptions, resource thresholds, and scaling readiness assessment. | Before Day 10 | Client to provide CPU/RAM/storage, OS, Docker/Fabric versions, exposed ports, and any runtime constraints. | Open
D-12 | Defect resolution ownership | Testing scope excludes implementation fixes | Required to avoid schedule impact during triage and retest. | Before Day 14 | Client to confirm dedicated implementation team for defect/gap resolution. | Open

## Scope Matrix
Test Area | Included Scope | Evidence / Output | Tools / Method | Notes and Exclusions
Functional | Web, mobile, backend API, database flows, user roles, consent workflows, and cross-service integration. | Executed test cases, screenshots/log extracts, API responses, defect records. | Manual test execution, curl, SQL queries, custom scripts. | Frontend/mobile source must be provided. Defect fixes are not in scope.
Security | SAST, secrets, dependency/image scan, endpoint exposure, TLS, authentication, authorization, API negative tests. | Tool outputs, request/response evidence, security findings register. | Semgrep CE, Gitleaks, Trivy, OWASP ZAP, testssl.sh, OpenSSL, curl. | Remediation and code changes are excluded unless separately agreed.
Blockchain | Fabric network startup, chaincode deployment, smart contract behavior, ledger integrity, consent state transitions, unauthorized access attempts. | Peer CLI/API evidence, ledger read/write evidence, negative test results. | Fabric peer CLI, Semgrep CE, custom negative-test scripts. | Requires complete Fabric test-network assets and identities.
Performance | Baseline API/Fabric load testing, concurrency behavior, resource usage, transaction throughput, response time summary. | Load test reports, logs, resource snapshots, bottleneck observations. | Hyperledger Caliper, custom load scripts, docker stats, logs. | Autoscaling validation requires Kubernetes or equivalent scaling environment.
Horizontal Scaling | Assess current environment against scaling requirement and identify whether the test environment supports autoscaling validation. | Scaling readiness note, risks, recommended environment changes. | Configuration review, container stats/logs, deployment review. | Docker Compose alone is not sufficient for autoscaling validation.
HIPAA | Control-oriented testing for access control, authentication, audit logging, transmission security, sensitive data exposure, and minimum necessary handling. | HIPAA checklist, test evidence, gap register. | Manual compliance checklist supported by security/API evidence. | Formal legal certification and remediation are excluded.
GDPR | Control-oriented testing for consent, personal data handling, access/deletion readiness, privacy-related workflows, retention indicators, and data minimization. | GDPR checklist, workflow evidence, gap register. | Manual compliance checklist supported by workflow/API evidence. | Formal legal certification and remediation are excluded.
Reporting | Daily/periodic status, defect register, evidence index, final report, unresolved risks, retest summary. | Status reports, final report, evidence pack. | Defect tracker, test logs, report compilation. | Retesting depends on fixes from the implementation team.