## Overview
EDR High-Level Testing Schedule
Reference schedule. Formal testing starts once missing setup artifacts, access, source code, configuration, and environment details are cleared.
Schedule basis | T0 is the first business day after all start-gate dependencies are cleared.
Overall window | Approximately 50 business days from T0, with selected phases running in parallel where feasible.
Planning approach | High-level schedule with generous buffers for environment stabilization, clarification cycles, evidence collection, and retesting.
Testing start | Testing execution should not begin until the missing technical details and setup artifacts are received and validated.
Remediation note | Resolution of any defects or gaps identified during testing is outside testing scope and requires a dedicated implementation team.
Primary outputs | Readiness note, test evidence, defect/gap register, compliance checklists, performance baseline, scaling readiness note, final report.
Phase | Window | Business Days | Main Area | Key Dependency | Output | Status | Notes
Dependency Closure | Pre-T0 / 5 business days | 5 | Readiness | Client responses and required artifacts. | Dependency tracker and testing start confirmation. | Planned | Testing start date is confirmed only after this phase is cleared.
Environment Setup and Smoke Validation | Days 1-5 | 5 | Setup | Docker Compose or equivalent runbook, Fabric assets, SQL dump, env files. | Environment readiness note and smoke test evidence. | Planned | Generous buffer included for setup fixes and clarification loops.
Test Planning and Traceability | Days 1-5 | 5 | Planning | Final requirements, confirmed runnable scope, test users. | Traceability matrix and high-level test cases. | Planned | Runs in parallel with environment setup.
Functional Testing | Days 6-15 | 10 | Functional | Runnable application stack, frontend/mobile source, seed data, test credentials. | Functional execution results and defects. | Planned | Covers manual web/mobile testing and API/database verification.
Blockchain and Smart Contract Testing | Days 10-18 | 9 | Blockchain | Complete Fabric test-network, connection profile, wallet identities, deployed chaincode. | Blockchain workflow evidence and smart contract findings. | Planned | Overlaps with functional testing once Fabric is stable.
Security Testing | Days 12-22 | 11 | Security | Complete source, package files, running endpoints, test users. | Security test evidence and security defect register. | Planned | Includes buffer for re-runs after environment corrections.
Performance and Load Baseline | Days 20-27 | 8 | Performance | Stable environment, agreed workload model, Caliper files or approved benchmark scripts. | Performance baseline results. | Planned | This is a baseline test, not production capacity certification.
Horizontal Scaling Readiness | Days 26-30 | 5 | Scalability | Infrastructure details and scaling target/thresholds. | Scaling readiness note and recommendations. | Planned | Autoscaling validation requires Kubernetes or equivalent scaling environment.
HIPAA and GDPR Compliance-Oriented Testing | Days 28-37 | 10 | Compliance | Stable workflows, logs/configuration access, documentation, test evidence from functional/security phases. | HIPAA/GDPR checklist and gap register. | Planned | Testing only. Formal certification and remediation are outside scope.
Defect Triage and Retesting Window | Days 35-44 | 10 | Retest | Dedicated implementation team available for defect/gap resolution. | Retest evidence and updated defect status. | Planned | Resolution of defects/gaps is not included in testing scope.
Final Reporting and Closure | Days 45-50 | 6 | Reporting | Testing execution complete and retest status agreed. | Final testing report and evidence pack. | Planned | Final dates may shift if environment or retest delays occur.

## Schedule
ID | Phase | Relative Window | Estimated Business Days | Stream | Included Scope | Entry Dependency | Output / Evidence | Notes | Status
P0 | Dependency Closure | Pre-T0 / 5 business days | 5 | Readiness | Close missing artifacts, environment details, access, source code gaps, seed data, Fabric setup details, and test credentials. | Client responses and required artifacts. | Dependency tracker and testing start confirmation. | Testing start date is confirmed only after this phase is cleared. | Planned
P1 | Environment Setup and Smoke Validation | Days 1-5 | 5 | Setup | Set up Docker/Fabric/MySQL/API/frontend/mobile environment, import seed data, validate startup order, and perform smoke checks. | Docker Compose or equivalent runbook, Fabric assets, SQL dump, env files. | Environment readiness note and smoke test evidence. | Generous buffer included for setup fixes and clarification loops. | Planned
P2 | Test Planning and Traceability | Days 1-5 | 5 | Planning | Finalize test scenarios, map BRD/SRS requirements, confirm roles, expected evidence, data needs, and pass/fail criteria. | Final requirements, confirmed runnable scope, test users. | Traceability matrix and high-level test cases. | Runs in parallel with environment setup. | Planned
P3 | Functional Testing | Days 6-15 | 10 | Functional | Validate web, mobile, backend API, database views, login, roles, patient/doctor/admin workflows, and cross-service integrations. | Runnable application stack, frontend/mobile source, seed data, test credentials. | Functional execution results and defects. | Covers manual web/mobile testing and API/database verification. | Planned
P4 | Blockchain and Smart Contract Testing | Days 10-18 | 9 | Blockchain | Validate Fabric network startup, chaincode deployment, ledger read/write behavior, consent workflow, unauthorized access attempts, and negative paths. | Complete Fabric test-network, connection profile, wallet identities, deployed chaincode. | Blockchain workflow evidence and smart contract findings. | Overlaps with functional testing once Fabric is stable. | Planned
P5 | Security Testing | Days 12-22 | 11 | Security | Run source, secret, dependency, container, TLS, endpoint, authentication, authorization, and API negative testing. | Complete source, package files, running endpoints, test users. | Security test evidence and security defect register. | Includes buffer for re-runs after environment corrections. | Planned
P6 | Performance and Load Baseline | Days 20-27 | 8 | Performance | Conduct baseline API and blockchain load tests, capture throughput, response time, errors, logs, and resource observations. | Stable environment, agreed workload model, Caliper files or approved benchmark scripts. | Performance baseline results. | This is a baseline test, not production capacity certification. | Planned
P7 | Horizontal Scaling Readiness | Days 26-30 | 5 | Scalability | Assess whether the provided environment supports scaling validation and document gaps where Docker Compose cannot prove autoscaling behavior. | Infrastructure details and scaling target/thresholds. | Scaling readiness note and recommendations. | Autoscaling validation requires Kubernetes or equivalent scaling environment. | Planned
P8 | HIPAA and GDPR Compliance-Oriented Testing | Days 28-37 | 10 | Compliance | Assess access control, audit logging, consent, data handling, privacy workflow readiness, sensitive data exposure, and retention indicators. | Stable workflows, logs/configuration access, documentation, test evidence from functional/security phases. | HIPAA/GDPR checklist and gap register. | Testing only. Formal certification and remediation are outside scope. | Planned
P9 | Defect Triage and Retesting Window | Days 35-44 | 10 | Retest | Support defect walkthroughs, retest fixes completed by the implementation team, update evidence, and track residual risks. | Dedicated implementation team available for defect/gap resolution. | Retest evidence and updated defect status. | Resolution of defects/gaps is not included in testing scope. | Planned
P10 | Final Reporting and Closure | Days 45-50 | 6 | Reporting | Prepare final report, executive summary, evidence index, unresolved risk register, recommendations, and closure walkthrough. | Testing execution complete and retest status agreed. | Final testing report and evidence pack. | Final dates may shift if environment or retest delays occur. | Planned

## Phase Timeline
ID | Phase | Stream | Pre-T0 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10
P0 | Dependency Closure | Readiness | bar: Pre-T0
P1 | Environment Setup and Smoke Validation | Setup | bar: Wk 1
P2 | Test Planning and Traceability | Planning | bar: Wk 1
P3 | Functional Testing | Functional | bar: Wk 2 to Wk 3
P4 | Blockchain and Smart Contract Testing | Blockchain | bar: Wk 2 to Wk 4
P5 | Security Testing | Security | bar: Wk 3 to Wk 5
P6 | Performance and Load Baseline | Performance | bar: Wk 4 to Wk 6
P7 | Horizontal Scaling Readiness | Scalability | bar: Wk 6
P8 | HIPAA and GDPR Compliance-Oriented Testing | Compliance | bar: Wk 6 to Wk 8
P9 | Defect Triage and Retesting Window | Retest | bar: Wk 7 to Wk 9
P10 | Final Reporting and Closure | Reporting | bar: Wk 9 to Wk 10

## Start Gate Dependencies
ID | Required Item | Current Finding | Why Needed | Required By | Status
D-01 | Docker Compose file or equivalent setup automation | Not present | Required to bring up MySQL, APIs, Fabric services, frontend/mobile support services, ports, volumes, and startup order. | Before T0 | Open
D-02 | Complete web frontend source code | bc-dentistry-frontend is empty | Required for web workflow and end-to-end testing. | Before T0 | Open
D-03 | Complete mobile application source code | BC-Dentistry-Mobile-App is empty | Required for patient consent and mobile workflow testing. | Before T0 | Open
D-04 | Complete Fabric test-network assets | network.sh references missing compose/configtx/organizations/bin/config assets | Required to start Fabric, create channel, deploy chaincode, and generate connection profile. | Before T0 | Open
D-05 | Validated SQL dump and seed/login data | datamodel2.sql has partial seed data and schema mismatch indicators | Required for login, roles, database views, repeatable functional tests. | Before T0 | Open
D-06 | Environment variables and sanitized configuration | .env examples exist but code also has hardcoded ports/hosts | Required for API, Fabric, DB, frontend, and mobile connectivity. | Before T0 | Open
D-07 | Confirmed test credentials | README lists users but seed records are not fully aligned | Required for Admin, Doctor, Patient, and consent workflow execution. | Before Day 5 | Open
D-08 | Caliper/workload files or approved workload model | caliper-benchmarks is empty | Required for repeatable performance testing. | Before Day 20 | Open
D-09 | Infrastructure details for running environment | Not included | Required for performance assumptions and scaling readiness assessment. | Before Day 20 | Open
D-10 | Defect resolution team confirmation | Testing scope excludes remediation | Required to support triage and retesting without blocking final reporting. | Before Day 35 | Open

## Testing Scope
Test Area | High-Level Scope | Tools / Method | Output
Functional | Web, mobile, backend API, database validation, roles, login, consent workflow, integrations. | Manual testing, curl/API scripts, SQL checks. | Functional test results and defect records.
Blockchain | Fabric startup, chaincode deployment, ledger operations, consent workflow, unauthorized and negative paths. | Fabric peer CLI, API scripts, Semgrep CE, custom negative-test scripts. | Blockchain evidence and smart contract findings.
Security | Source scan, secrets, dependencies, containers, TLS, endpoints, authentication, authorization, API negative tests. | Semgrep CE, Gitleaks, Trivy, OWASP ZAP, testssl.sh, OpenSSL, curl. | Security evidence and defect register.
Performance | Baseline API and blockchain load behavior, response times, errors, throughput, resource observations. | Hyperledger Caliper, custom load scripts, docker stats/logs. | Performance baseline report.
Horizontal Scaling | Readiness assessment for autoscaling validation and Docker Compose limitations. | Configuration/infrastructure review, container observations. | Scaling readiness note.
HIPAA | Access control, authentication, audit logging, transmission security, sensitive data exposure, minimum necessary handling. | Manual compliance checklist supported by test evidence. | HIPAA checklist and gaps.
GDPR | Consent, personal data handling, data access/deletion readiness, privacy workflow readiness, retention indicators. | Manual compliance checklist supported by workflow evidence. | GDPR checklist and gaps.
Reporting | Status updates, defect/gap register, retest evidence, final report, evidence index, residual risks. | Report compilation and defect tracker review. | Final test report and evidence pack.